## Prototype Development
Prototype Development
Task NO | Task Description | Start Date | End Date | Length
1 | Research system requirements & Context | 2025-08-20 | 2025-08-23 | 3
2 | Draft design rationale (documentation) | 2025-08-23 | 2025-08-25 | 2
3 | Database UML diagram (tables & relations | 2025-08-24 | 2025-08-26 | 2
4 | Project plan creation (timeline & task) | 2025-08-26 | 2025-08-27 | 1
5 | GUI prototype - Lecture side | 2025-08-27 | 2025-08-29 | 2
6 | GUI prototype - Coordinator & Manager | 2025-08-29 | 2025-08-31 | 2
7 | Document assumptions & constraints | 2025-08-31 | 2025-09-01 | 1
8 | Github commits & version control updates | 2025-08-20 | 2025-09-01 | 12
9 | Consolidate draft report for submission | 2025-09-01 | 2025-09-03 | 2